## Sheet1
List of features | No. of Hours
Prepare HTML Design (Header, Footer, Filters, Excel Integration) | 24
Integrate HTML with Node/Angular | 12
Prepare SQL queries & get Dropdowns data, cascading dropdowns and testing | 24
Get Data Button click to load the data from database to excel | 30
Implement or test how the get data logic is working for all the templates. If something is not working as expected then need to work on that | 24
Apply filters on the downloaded data, update the data set and bind it to excel | 24
Show or hide dimensions | 24
Dynamic implementation for editable months | 16
Uploading data to database (write sql query, validate and test it) | 30
Database setup | 14
Preparing schema and validating | 12
Create table scripts, run & validate them by inserting dummy data | 12
Testing and validating all the features - Internal testing | 24
External Testing | 18
Power BI Analysis, Implementation, testing and validation | 60
No.Of Days | 58

## Sheet2
Schema
tblExtract |  |  | tblDimFactData |  |  | tblScenario
Column Name | Data Type | Constraint | Column Name | Data Type | Constraint | Column Name | Data Type | Constraint
ExtractID | INT | Primary Key Identity(1,1) | DimFactID | INT | Primary Key Identity(1,1) | ScenarioID | INT | Primary Key Identity(1,1)
[Category] | NVARCHAR(200) | NOT NULL | Column01 | NVARCHAR(200) |  | ScenarioName | NVARCHAR(500) | NOT NULL
[Period] | INT | NOT NULL | Column02 | NVARCHAR(200) |  | ScenarioFilters | NVARCHAR(MAX)
[Year] | INT | NOT NULL | Column03 | NVARCHAR(200) |  | IsActive | BIT | DEFAULT 1
[4wk Period] | DATE TIME | NOT NULL | Column04 | NVARCHAR(200) |  | CreatedDate | DATE TIME | DEFAULT GET DATE()
[week] | DATE TIME | NOT NULL | Column05 | NVARCHAR(200) |  | CreatedBy | NVARCHAR(100) | DEFAULT 'SYSTEM'
[SubCategory] | NVARCHAR(200) | NOT NULL | Column06 | NVARCHAR(200) |  | UpdatedDate | DATE TIME | DEFAULT GET DATE()
[Source] | NVARCHAR(200) | NOT NULL | Column07 | NVARCHAR(200) |  | UpdatedBy | NVARCHAR(100) | DEFAULT 'SYSTEM'
[Brand] | NVARCHAR(200) | NOT NULL | Column08 | NVARCHAR(200)
[ULDollarSales] | Decimal(12,5) |  | Column09 | NVARCHAR(200)
[TTLDollarSales] | Decimal(12,5) |  | Column10 | NVARCHAR(200)
IsActive | BIT | DEFAULT 1 | Column11 | DECIMAL(12,5)
CreatedDate | DATE TIME | DEFAULT GET DATE() | Column12 | DECIMAL(12,5)
CreatedBy | NVARCHAR(100) | DEFAULT 'SYSTEM' | Column13 | DECIMAL(12,5)
UpdatedDate | DATE TIME | DEFAULT GET DATE() | Column14 | DECIMAL(12,5)
UpdatedBy | NVARCHAR(100) | DEFAULT 'SYSTEM' | Column15 | DECIMAL(12,5)
|  |  | Column16 | DECIMAL(12,5)
|  |  | Column17 | DECIMAL(12,5)
tblColumns |  |  | Column18 | DECIMAL(12,5)
Column Name | Data Type | Constraint | Column19 | DECIMAL(12,5)
ColumnID | INT | Primary Key Identity(1,1) | Column20 | DECIMAL(12,5)
Column | NVARCHAR(100) | NOT NULL | Column21 | DECIMAL(12,5)
DisplayName | NVARCHAR(200) |  | Column22 | DECIMAL(12,5)
SortOrder | BIT |  | Column23 | DECIMAL(12,5)
IsActive | BIT | DEFAULT 1 | Column24 | DECIMAL(12,5)
CreatedDate | DATE TIME | DEFAULT GET DATE() | Column25 | DECIMAL(12,5)
CreatedBy | NVARCHAR(100) | DEFAULT 'SYSTEM' | Column26 | DECIMAL(12,5)
UpdatedDate | DATE TIME | DEFAULT GET DATE() | Column27 | DECIMAL(12,5)
UpdatedBy | NVARCHAR(100) | DEFAULT 'SYSTEM' | Column28 | DECIMAL(12,5)
|  |  | Column29 | DECIMAL(12,5)
|  |  | Column30 | DECIMAL(12,5)
|  |  | Column31 | DECIMAL(12,5)
|  |  | Column32 | DECIMAL(12,5)
|  |  | Column33 | DECIMAL(12,5)
|  |  | Column34 | DECIMAL(12,5)
|  |  | Column35 | DECIMAL(12,5)
|  |  | Column36 | DECIMAL(12,5)
|  |  | Column37 | DECIMAL(12,5)
|  |  | Column38 | DECIMAL(12,5)
|  |  | Column39 | DECIMAL(12,5)
|  |  | Column40 | DECIMAL(12,5)
|  |  | IsActive | BIT | DEFAULT 1
|  |  | CreatedDate | DATE TIME | DEFAULT GET DATE()
|  |  | CreatedBy | NVARCHAR(100) | DEFAULT 'SYSTEM'
|  |  | UpdatedDate | DATE TIME | DEFAULT GET DATE()
|  |  | UpdatedBy | NVARCHAR(100) | DEFAULT 'SYSTEM'